## List
Dashboard Project
Team Pear Timeline
DATE | ACHIEVEMENTS | NOTES
STAGE 1 TIMELINE
September 30th, 2015 | Met group members | Met members, exchanged contact info
September 30th, 2015 | Came up with meeting times | Used Doodle poll
September 30th, 2015 | Set up Git repository for team
September 30th, 2015 | Came up with questions | decided on requirements questions to ask
October 1st, 2015 | Submitted requirements questions | submitted them on OWL
October 6th, 2015 | Development tasks + initial plans determined | decided to present publications using pie chart visualization
October 7th, 2015 | Presented initial plans | presented design plans and task allocation to Professor Madhavji
October 13th, 2015 | Decided on system design for project | decided to use the MVC model for the project
October 13th, 2015 | Decided on roles according to design | assigned members to view, model, controller
October 14th, 2015 | Wrote header files | ie professorMap.h
October 15th, 2015 | Came up with and submitted questions | came up with systems question and submitted them on OWL
October 17th, 2015 | Assigned functions and files to people
October 18th, 2015 | Came up with use case diagrams and UML diagrams
October 23rd, 2015 | Implemented functions and files | ie professorMap.cpp
October 25th, 2015 | Debugged the project files
October 26th, 2015 | Integrated the project and tested | put together the model, view, controller parts of the project
October 26th, 2015 | Finshed deliverables
October 26th, 2015 | Submitted stage 1
STAGE 2 PLANS
October 30th, 2015 | Come up with sequence diagrams for scenario
October 30th, 2015 | Come up with package diagrams
November 2nd, 2015 | Did graphical representation of design pattern
November 5th, 2015 | Implement teaching spreadsheet
November 6th, 2015 | Implement presentations given spreadsheet
November 7th, 2015 | Implement grants obtained spreadsheet
November 10th, 2015 | Implement graphical layouts for each of the spreadsheet
November 16th, 2015 | Debug project and testing
November 18th, 2015 | Improve system and improve efficiency
November 19th, 2015 | Decide on strech requirements if any
November 20th, 2015 | Implement strech requirements
November 22nd, 2015 | Debug program to get working program
November 24th, 2015 | Explain the system
November 24th, 2015 | Finsh deliverables
November 25th, 2015 | Submitted stage 2
FINAL SUBMISSION ABSTRACT PLAN
Finish any unfinished implementations
Unit testing and document test cases
| Finish system design | update case, class, sequence, and package diagrams
Inspect program using OO metrics
Write retrospective analysis
Create title page
Create table of contents
Update development plans from stage 2
December 9th, 2015 | Submit project for the final submission